## Issues
Item # | Status | Associated Design Entity | Issue Type | Brief Description | Resource | Date identified | Plan date to resolve | Date of last update | Status of resolution / comments
1 | Complete | File upload/Download function | I: Issue | Upload successfully | Different types of files(doc, docx, txt, jpg, py files) | 2019-06-12 | 2019-06-12 | 2019-06-12 | Complete
2 | Complete | File upload/Download function | I: Issue | Download successfully | Login system and accounts | 2019-06-12 | 2019-06-12 | 2019-06-12 | Complete
3 | Complete | Login function | A: Action Item | Invalid username or password | Username and password | 2019-06-12 | 2019-06-12 | 2019-06-13 | Complete
4 | Complete | The interaction between uploading files and database | A: Action Item | The file contents are incomplete | Incompleted files | 2019-06-12 | 2019-06-12 | 2019-06-13 | Complete
5 | Complete | The interaction between login function and database | I: Issue | Accounts matching failed | Accounts and database | 2019-06-12 | 2019-06-12 | 2019-06-13 | Complete
6 | Complete | The interaction between the downloading file and database | I: Issue | Download file matching error | Downloaded files and database | 2019-06-12 | 2019-06-12 | 2019-06-13 | Complete
7 | Complete | Stress testing | A: Action Item | Unable to login | Login system, accounts and users | 2019-06-12 | 2019-06-13 | 2019-06-13 | Complete
8 | Complete | Stress testing | A: Action Item | Unable to upload file | Files, database and users | 2019-06-12 | 2019-06-13 | 2019-06-13 | Complete
9 | Complete | Stress testing | A: Action Item | Unable to download file | Flies, database and users | 2019-06-12 | 2019-06-13 | 2019-06-13 | Complete
10 | Complete | Reward score function | I: Issue | The reward score unable to work | Files, database and users | 2019-06-12 | 2019-06-13 | 2019-06-13 | Complete
11 | Complete | File upload/Download function | I: Issue | two users unable to upload files | Files, database and users | 2019-06-13 | 2019-06-13 | 2019-06-14 | Complete
12 | Complete | Language of Buttons | I: Issue | the language is Chinese | Files, database and users | 2019-06-13 | 2019-06-15 | 2019-06-15 | Complete
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete