## Sheet1
Modules | Completion Degree | Uncompleted part
Main Page Layout | 100% | None
Login and Registration Module | 100% | None
File upload and download module | 90% | The problem that the filename with '.', '-' cannot be uploaded has not been solved yet
User Comment Module | 0% | This part hadn't been revolved during development process, we'll add it later
File Search Module | 0% | This part hadn't been revolved during development process, we'll add it later
Database Construction | 100% | None
Integral System Based on Point Praise and Download Quantity | 95% | No effective mothed to prevent repetitive likes or downloads
Mall shopping module | 100% | None
Database Construction | 100% | None
Administrator Interface | 50% | The administrator interface hasn't been well-designed and access to the website system